## Summary
Milestone 3 - Team Lead Dashboard Review Tracker
Hospital analytics project ¦ Review of 4 member dashboards
Dashboard | Member | Tool | Items | Not reviewed | OK | Issue found | Fixed | % reviewed
Hospital Overview | Member 2 | Tableau | 8 | 0 | 0 | 8 | 0
Patient Flow | Member 3 | Python (Colab/Plotly) | 12 | 0 | 0 | 12 | 0
Department Analytics | Member 4 | Tableau | 7 | 0 | 0 | 7 | 0
Resource Utilization | Member 5 | Power BI | 16 | 0 | 0 | 16 | 0
Total
Total |  |  | 43 | 0 | 0 | 43 | 0
Integration checks
Total checks
Pass / Fixed
Fail
Not checked
Open issues in Issues Log
Review conclusion
Structural/file review completed for the uploaded Member 2, 3, 4 and 5 artifacts. Independent numeric reconciliation remains blocked because the underlying source CSV dataset (including patient_flow_dataset.csv) was not supplied, and embedded Tableau Hyper/Power BI data could not be independently queried in this environment.
Notes marked with observations (e.g. definition differences, duplicate visuals) come from reading the files and should be confirmed.
Summary counts update automatically from the other sheets. In the Issues Log, the first (grey italic) row is an example - overwrite or ignore it.

## Review Tracker
# | Dashboard | Member | Tool | Type | KPI / Chart | Found in file | Review status | Reviewer notes / observations
1 | Hospital Overview | Member 2 | Tableau | KPI | Total Admissions | Yes | Reviewed – numeric check blocked
2 | Hospital Overview | Member 2 | Tableau | KPI | Average LOS | Yes | Reviewed – numeric check blocked | Compare definition with Member 3 'Average Stay' and Member 4 'LOS'
3 | Hospital Overview | Member 2 | Tableau | KPI | Readmission Rate | Yes | Issue found | Also shown by Member 4 - values should match Readmission formula is present, but its numeric result could not be independently recalculated from the embedded Hyper extract.
4 | Hospital Overview | Member 2 | Tableau | KPI | Bed Utilization Rate | Yes | Issue found | Separate sheet from Occupancy Rate - confirm the two are defined differently Workbook defines Occupancy Rate and Bed Utilization Rate with the same formula; they are not demonstrably different.
5 | Hospital Overview | Member 2 | Tableau | KPI | Occupancy Rate | Yes | Reviewed – numeric check blocked | Also shown by Member 4 - values should match
6 | Hospital Overview | Member 2 | Tableau | Chart | Monthly Admissions | Yes | Reviewed – numeric check blocked
7 | Hospital Overview | Member 2 | Tableau | Chart | Monthly Discharges | Yes | Reviewed – numeric check blocked
8 | Hospital Overview | Member 2 | Tableau | Chart | Admissions vs Discharges | Yes | Issue found | Also shown by Member 4 (by department) - totals should reconcile Source CSV patient_flow_dataset.csv is not included among the uploaded files, so the KPI value cannot be independently recalculated.
9 | Patient Flow | Member 3 | Python (Colab/Plotly) | KPI | Admissions | Yes | Issue found | Source CSV patient_flow_dataset.csv is not included among the uploaded files, so the KPI value cannot be independently recalculated.
10 | Patient Flow | Member 3 | Python (Colab/Plotly) | KPI | Discharges | Yes | Issue found | Source CSV patient_flow_dataset.csv is not included among the uploaded files, so the KPI value cannot be independently recalculated.
11 | Patient Flow | Member 3 | Python (Colab/Plotly) | KPI | Transfers | Yes | Issue found | Source CSV patient_flow_dataset.csv is not included among the uploaded files, so the KPI value cannot be independently recalculated.
12 | Patient Flow | Member 3 | Python (Colab/Plotly) | KPI | Unique Patients | Yes | Issue found | Code calculates Average Stay as mean duration_in_department_hours, which is not whole-admission LOS.
13 | Patient Flow | Member 3 | Python (Colab/Plotly) | KPI | Average Stay | Yes | Issue found | Calculated as mean of duration_in_department_hours (time per department stay), not whole-admission LOS - not comparable to Member 2's Average LOS Patient Volume is movement-record count, not distinct-patient count.
14 | Patient Flow | Member 3 | Python (Colab/Plotly) | Chart | Patient Volume Over Time | Yes | Reviewed – numeric check blocked | 'Volume' counts movement records, not distinct patients
15 | Patient Flow | Member 3 | Python (Colab/Plotly) | Chart | Admissions, Discharges and Transfers | Yes | Reviewed – numeric check blocked
16 | Patient Flow | Member 3 | Python (Colab/Plotly) | Chart | Patient Volume by Department | Yes | Reviewed – numeric check blocked
17 | Patient Flow | Member 3 | Python (Colab/Plotly) | Chart | Average Department Stay | Yes | Reviewed – numeric check blocked
18 | Patient Flow | Member 3 | Python (Colab/Plotly) | Chart | Patient Volume by Hour | Yes | Reviewed – numeric check blocked
19 | Patient Flow | Member 3 | Python (Colab/Plotly) | Chart | Patient Volume by Shift | Yes | Issue found | Chart title says Admissions vs Discharges, but the plotted data also contains Transfers.
20 | Patient Flow | Member 3 | Python (Colab/Plotly) | Chart | Admissions vs Discharges by Department | Yes | Reviewed – numeric check blocked | Chart title omits Transfers, but the data includes all three movement types - fix title or filter
21 | Department Analytics | Member 4 | Tableau | Chart | Cmp - Admissions vs Discharges | Yes | Reviewed – numeric check blocked | Reconcile with Member 2 totals
22 | Department Analytics | Member 4 | Tableau | Chart | Cmp - Capacity vs Occupancy | Yes | Reviewed – numeric check blocked
23 | Department Analytics | Member 4 | Tableau | Chart | Cmp - LOS | Yes | Reviewed – numeric check blocked | Reconcile with Member 2 Average LOS
24 | Department Analytics | Member 4 | Tableau | Chart | Cmp - Occupancy | Yes | Reviewed – numeric check blocked | Reconcile with Member 2 Occupancy Rate
25 | Department Analytics | Member 4 | Tableau | Chart | Cmp - Readmission | Yes | Issue found | Reconcile with Member 2 Readmission Rate Efficiency Ranking uses an efficiency-related field, but no explicit formula is documented in the workbook review material.
26 | Department Analytics | Member 4 | Tableau | Chart | Cmp - Staff Ratio | Yes | Issue found | Workbook/dashboard name is 'Hospital Operations Dashboard' rather than the milestone name.
27 | Department Analytics | Member 4 | Tableau | Chart | Efficiency Ranking | Yes | Reviewed – numeric check blocked | Check ranking formula is documented
28 | Resource Utilization | Member 5 | Power BI | KPI | Units in Use | Yes | Reviewed – numeric check blocked
29 | Resource Utilization | Member 5 | Power BI | KPI | Utilization Rate % | Yes | Reviewed – numeric check blocked
30 | Resource Utilization | Member 5 | Power BI | KPI | Total Units Available | Yes | Reviewed – numeric check blocked
31 | Resource Utilization | Member 5 | Power BI | KPI | Utilized Hours | Yes | Reviewed – numeric check blocked
32 | Resource Utilization | Member 5 | Power BI | Chart | Downtime Hours by Department | Yes | Reviewed – numeric check blocked
33 | Resource Utilization | Member 5 | Power BI | Chart | Resource Type by Count (bar) | Yes | Issue found | Power BI model contains resource_utilization_dataset, but this source is not part of the original hospital CSV set identified in the report.
34 | Resource Utilization | Member 5 | Power BI | Chart | Total Units Available by Department | Yes | Reviewed – numeric check blocked
35 | Resource Utilization | Member 5 | Power BI | Chart | Utilization Rate over Time (line) | Yes | Reviewed – numeric check blocked | A second line chart with the same fields exists - check whether intentional
36 | Resource Utilization | Member 5 | Power BI | Chart | Utilization Rate over Time (line, 2nd) | Yes | Issue found | Possible duplicate of the line chart above Potential duplicate utilization visuals remain; visual definitions use overlapping fields and should be confirmed as intentional.
37 | Resource Utilization | Member 5 | Power BI | Chart | Utilized Hours & Rate by Department (combo) | Yes | Issue found | A second combo chart with the same fields exists - check whether intentional Potential duplicate utilization visuals remain; visual definitions use overlapping fields and should be confirmed as intentional.
38 | Resource Utilization | Member 5 | Power BI | Chart | Utilized Hours & Rate by Department (combo, 2nd) | Yes | Reviewed – numeric check blocked | Possible duplicate of the combo chart above
39 | Resource Utilization | Member 5 | Power BI | Chart | Capacity vs Utilized Hours (scatter) | Yes | Reviewed – numeric check blocked
40 | Resource Utilization | Member 5 | Power BI | Chart | Resource Type Share (pie) | Yes | Reviewed – numeric check blocked
41 | Resource Utilization | Member 5 | Power BI | Chart | Utilization Rate by Resource Type | Yes | Reviewed – numeric check blocked
42 | Resource Utilization | Member 5 | Power BI | Chart | Utilization Rate by Department | Yes | Reviewed – numeric check blocked
43 | Resource Utilization | Member 5 | Power BI | Filter | Department slicer | Yes | Reviewed – numeric check blocked | Confirm it filters all visuals on the page

## Integration Checks
# | Check | Dashboards involved | What to verify | Status | Notes
1 | KPI definition: Length of Stay | Overview, Patient Flow, Dept Analytics | Same formula (discharge - admission) and unit (days vs hours). Patient Flow uses hours per department stay. | Issue found | Member 3 Average Stay is department-stay hours; Member 2 Average LOS is whole-admission LOS in the Tableau workbook. They are not the same KPI definition.
2 | KPI definition: Occupancy / bed utilization | Overview, Dept Analytics | Same numerator/denominator; Overview has both Bed Utilization and Occupancy - confirm they differ on purpose. | Issue found | Overview workbook contains identical formulas for Occupancy Rate and Bed Utilization Rate; they are not differentiated.
3 | KPI definition: Readmission rate | Overview, Dept Analytics | Same readmission window and population. | Reviewed – numeric check blocked | Definitions/formulas could not be fully reconciled because the underlying datasets and numeric outputs were not available for independent recalculation.
4 | Admissions vs Discharges totals | Overview, Patient Flow, Dept Analytics | Overall and department-level counts reconcile with admission.csv (45,000 admissions in source). | Reviewed – numeric check blocked | The uploaded files show the relevant KPIs/charts, but the source datasets needed for a fresh reconciliation were not supplied/readable.
5 | Data source availability | Patient Flow, Resource Utilization | patient_flow_dataset.csv and the resource-utilization table are not in the original dataset zip - confirm where they come from and that they are in the shared data folder. | Issue found | Patient Flow requires patient_flow_dataset.csv; Resource Utilization uses resource_utilization_dataset inside the PBIX. Neither was supplied as the original shared dataset.
6 | Data source consistency | Overview, Dept Analytics | Both use member-prepared cleaned files rather than the raw CSVs - confirm cleaning steps are documented. | Reviewed – numeric check blocked | Member 2 and Member 4 use prepared data/extracts; the cleaning lineage cannot be independently validated without the raw source dataset.
7 | Department names | All | Same department names/spelling across dashboards so departments can be compared. | Reviewed – numeric check blocked | Department names can be inspected in workbook metadata, but cross-dashboard row-level comparison was not possible without the common source data.
8 | Date range | All | Same reporting period on every dashboard. | Reviewed – numeric check blocked | Date fields are present, but common reporting-period equality was not independently recalculated.
9 | Titles and naming | All | Dashboard titles match the milestone names (Member 4's dashboard is titled 'Hospital Operations Dashboard'; Member 5's page is 'time and efficiency analysis'). | Issue found | Member 4 is titled 'Hospital Operations Dashboard'; Member 5 page is named 'time and efficiency analysis'.
10 | Visual consistency | All | Common colour palette, fonts and KPI card style across the 4 dashboards (tools differ: Tableau, Python, Power BI). | Issue found | Tools and styling differ; a common visual convention has not been demonstrated.
11 | Filters / interactivity | All | Slicers and filters work and affect all relevant visuals. | Reviewed – numeric check blocked | Filters/slicers are present in the files, but interactive behavior could not be executed here.
12 | Runs outside author's machine | Patient Flow | Script uses Colab-only calls (files.upload, !pip install) - needs a Colab run or a cleaned script. | Issue found | Member 3 script explicitly uses Colab-only files.upload and !pip install commands.

## Issues Log
ID | Dashboard | Member | Issue description | Severity | Status | Date found | Date fixed | Fix / resolution
EXAMPLE | Patient Flow | Member 3 | Chart title says 'Admissions vs Discharges' but chart also shows Transfers | Low | Open